## Project Tracker
Project List
Project | Category | Estimated Cost | Project Cost | Completion Date | Bid Opening | Award Date | Notes
Project 1 | 536 Well Field - Well Sites | 5429000 | 0 | 2/29/2023 | 00/00/0000 | 00/00/0000 | This project consists of 5 water production wells, collection piping, roadways, and electrical connections
Project 2 | 536 Well Field - Transmission | 2685000 | 0 | 02/29/2023 | 2022-04-22 | 2022-05-03 | This project consists of a 1,000,000-gallon ground storage tank. The 16-inch transmission pipeline would connect to the existing transmission pipeline at County Road 182 and extend approximately 1-1/2 miles to the 536 property.
Project 3 | Airport Pump Station Expansion Project | 0 | 3797061.5 | 2023-09-06 | 2021-11-22 | 2021-12-07 | The project provides a new 1,000,000-gallon ground storage tank (GST), a new pump station with piping, valves, and equipment at the Airport Pump Station in preparation for development of the 536 Well Field. The GST and pump station will provide the state-required water storage and will offset and allow for the decommissioning of the 750,000-gallon Paddock GST.
Project 4 | Eastside Sewer | 0 | 16300000 | 2024-03-31 | 00/00/0000 | 2018-08-21 | The Eastside Sewer project will provide a sanitary sewer main and laterals to areas generally east and north in the City of Stephenville. The project name comes from the proposed utility layout following the east side of the Bosque River. The project will eliminate a critical capacity burden on the existing sanitary sewer collection system and simultaneously serve potential developments of approximately 19,000 acres (30 square miles) east, north and northwest of the current service area. The construction of the proposed collector system will be structured in phases: Lift Station Completed on 6/16/2020 for the amount of $4,437,000.00; Phase 1 (Load Transfer Phase); Phase 2 (Airport Expansion Phase); and Phase 3 (281 Corridor Phase)
Project 5 | Harbin Drive Improvements | 0 | 10097474.5 | 2023-09-11 | 2021-09-28 | 2021-10-04 | The Harbin Drive Improvements Project consists of the widening of Harbin Drive from W. Washington St. to the Northwest Loop. The existing 2-lane section will be improved to a 4-lane divided street with 10-ft wide sidewalk on the east side of Harbin. The existing water and wastewater lines will be replaced. Storm drain improvements along Harbin, Tarleton St., and Saint Felix Ave.
Project 6 | Hyman, Swan, and S. Dale Resurfacing Project | 0 | 271839.25 | 2022-07-31 | 2022-03-09 | 2022-04-05 | This project is the resurfacing of existing streets within the City of Stephenville.
Project 7 | Long Street Improvements | 0 | 594700 | 2023-08-31 | 00/00/0000 | 2021-09-07 | This project includes the reconstruction of W. Long Street from Alexander Rd. to Graham Ave. This project will replace or add the existing pavement, curb, sidewalks, and curb ramps on both sides of the street to meet accessibility requirements. Existing water and wastewater lines will be replaced.
Project 8 | Lockhart Road Improvements | 0 | 320000 | 2023-10-31 | 00/00/0000 | 2021-09-03 | This project is for improvements to Lockhart Road at FWRR. The existing roadway will be realigned at the railroad crossing, including culvert replacements.
Project 9 | TWDB FIF - Flood Infrastructure Funding | 0 | 450000 | 2022-12-17 | 00/00/0000 | 2020-12-17 | The City of Stephenville will be performing a watershed study of the Green Creek-North Bosque River Watershed (Hydrologic Unit Code 1206020401), also referred to as the North Bosque River Watershed in accordance with the requirements of the Flood Infrastructure Fund (FIF) Category 1. The FIF is managed by the Texas Water Development Board (TWDB) and it was created to assist in the financing of drainage, flood mitigation and flood control projects. The watershed study will include the development of hydrologic and hydraulic models that will serve as planning tool to define flood hazard risks for private properties and public infrastructure. The models will also provide a platform for developing and evaluating improvement alternatives. A dam safety assessment of NRCS dam structures will also be performed and include visual condition assessments and breach analyses.